## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[6 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Milestone: Project Initiation
Research data points on reservation systems and enhancement | 2020-01-10 | 2020-01-17 | 7 | CARTER | 100% | bar: WEEK 1 W to WEEK 2 F; WEEK 5 M to WEEK 5 T
Gather historical data on booking process | 2020-01-15 | 2020-01-15 | 1 | PETA | 100% | bar: WEEK 2 T; WEEK 2 R to WEEK 2 F; WEEK 5 M to WEEK 5 T
Align and evaluate stakeholders | 2020-01-15 | 2020-01-17 | 3 | OMAR | 100% | bar: WEEK 2 T to WEEK 2 F; WEEK 5 M to WEEK 5 T
Calculate projections and enhancements | 2020-01-17 | 2020-01-18 | 2 | DEANNA | 100% | bar: WEEK 2 T; WEEK 2 R to WEEK 2 F; WEEK 5 M to WEEK 5 T
Interview members of the staff | 2020-01-18 | 2020-01-19 | 1 | SEYDOU | 100% | bar: WEEK 2 T; WEEK 2 R to WEEK 3 M; WEEK 5 M to WEEK 5 T
Create project charter (scope and goals) | 2020-01-22 | 2020-01-26 | 4 | OMAR | 100% | bar: WEEK 2 T; WEEK 2 R to WEEK 2 F; WEEK 3 T to WEEK 3 F; WEEK 5 M to WEEK 5 T
Schedule kick off meeting | 2020-01-29 | 2020-01-29 | 1 | DEANNA | 100% | bar: WEEK 2 T; WEEK 2 R to WEEK 2 F; WEEK 3 F; WEEK 5 M to WEEK 5 T
Milestone: Procurement
Identify number of tablets needed | 2020-01-10 | 2020-02-09 | 2 | CARTER | 100% | bar: WEEK 2 T; WEEK 2 R to WEEK 2 F; WEEK 4 M to WEEK 4 T; WEEK 5 M to WEEK 5 T
Identify number of tablets needed | 2020-01-10 | 2020-02-09 | 2 | PETA | 100% | bar: WEEK 2 T; WEEK 2 R to WEEK 2 F; WEEK 4 T to WEEK 4 W; WEEK 5 M to WEEK 5 T
Create contract and statements of work for tablet vendor | 2020-01-10 | 2020-02-10 | 1 | OMAR | 100% | bar: WEEK 2 T; WEEK 2 R to WEEK 2 F; WEEK 4 W; WEEK 5 M to WEEK 5 T
Research reservation system options | 2020-02-02 | 2020-02-02 | 4 | DEANNA | 100% | bar: WEEK 2 T; WEEK 2 R to WEEK 2 F; WEEK 4 W to WEEK 5 T
Generate quotes and review costs | 2020-02-05 | 2020-02-05 | 3 | SEYDOU | 100% | bar: WEEK 2 T; WEEK 2 R to WEEK 2 F; WEEK 4 F to WEEK 5 T
Test out reservation systems | 2020-02-05 | 2020-02-09 | 4 | OMAR | 100% | bar: WEEK 2 T; WEEK 2 R to WEEK 2 F; WEEK 4 F to WEEK 5 W
Choose a reservation system | 2020-02-05 | 2020-02-09 | 4 | DEANNA | 100% | bar: WEEK 2 T; WEEK 2 R to WEEK 2 F
Vendor timeline and deliverables schedule | 2020-02-06 | 2020-02-10 | 5 | SEYDOU | 100% | bar: WEEK 2 T; WEEK 2 R to WEEK 2 F; WEEK 5 M to WEEK 5 T; WEEK 6 M to WEEK 6 F
Milestone: Installation
Connect marketing team with Terrific Tablets for branding and digital menu design | 2020-03-01 | 2020-03-06 | 1 | OMAR | 100% | bar: WEEK 2 T; WEEK 2 R; WEEK 5 M to WEEK 5 T; WEEK 7 M
Work with Carter on possible menu revamp | 2020-03-02 | 2020-03-07 | 10 | DEANNA | 100% | bar: WEEK 2 T; WEEK 2 R; WEEK 5 M to WEEK 5 T; WEEK 7 T to WEEK 9 T
Add featured menu items and coupon values to tablets | 2020-03-03 | 2020-03-08 | 1 | SEYDOU | 100% | bar: WEEK 2 T; WEEK 2 R; WEEK 5 M to WEEK 5 T; WEEK 9 T
Work with tablet supplier to identify common issues and turn-around times resolving tablet problems. | 2020-03-04 | 2020-03-09 | 2 | OMAR | 100% | bar: WEEK 2 T; WEEK 2 R; WEEK 5 M to WEEK 5 T; WEEK 9 W to WEEK 9 R
Develop internal policy and troubleshooting guides for the tablet rollout and usage | 2020-03-05 | 2020-03-10 | 3 | DEANNA | 100% | bar: WEEK 2 T; WEEK 2 R to WEEK 2 F; WEEK 5 M to WEEK 5 T; WEEK 9 R to WEEK 10 M
Assess work required to ensure tablets integrate seamlessly with existing POS and host system | 2020-03-06 | 2020-03-11 | 3 | SEYDOU | 100% | bar: WEEK 2 T; WEEK 2 R to WEEK 2 F; WEEK 5 M to WEEK 5 T; WEEK 9 R to WEEK 10 T
Milestone: Training
Create a training program | 2020-04-19 | 2020-04-24 | 6 | PETA | 100% | bar: WEEK 2 T; WEEK 2 R to WEEK 2 F; WEEK 5 M to WEEK 5 T
Map out seating chart/upload into software | 2020-04-20 | 2020-04-25 | 2 | PETA | 100% | bar: WEEK 2 T; WEEK 2 R to WEEK 2 F; WEEK 5 M to WEEK 5 T; WEEK 10 T to WEEK 10 W
Train GMs on new software | 2020-04-21 | 2020-04-26 | 2 | PETA | 100% | bar: WEEK 2 T; WEEK 2 R to WEEK 2 F; WEEK 5 M to WEEK 5 T; WEEK 10 R
Train staff on new software | 2020-04-22 | 2020-04-27 | 2 | PETA | 100% | bar: WEEK 2 T; WEEK 2 R to WEEK 2 F; WEEK 5 M to WEEK 5 T; WEEK 10 F
Test run reservation system | 2020-04-23 | 2020-04-28 | 2 | PETA | 100% | bar: WEEK 2 T; WEEK 2 R to WEEK 2 F; WEEK 5 M to WEEK 5 T; WEEK 11 M
Create troubleshoot/support plan | 2020-04-24 | 2020-04-29 | 5 | SEYDOU | 100% | bar: WEEK 2 T; WEEK 2 R to WEEK 2 F; WEEK 5 M to WEEK 5 T; WEEK 10 T to WEEK 11 M
Milestone: Launch |  |  |  |  | 100%
Schedule launch day | 2020-05-24 | 2020-05-24 | 1 | OMAR | 100% | bar: WEEK 11 T
Execute rollout | 2020-05-25 | 2020-05-25 | 1 | SEYDOU | 100% | bar: WEEK 11 W
Monitor | 2020-05-25 | 2020-05-31 | 10 | CARTER | 100% | bar: WEEK 11 T to WEEK 12 F

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Initiation
Research data points on electronic ordering |  | 2.3333 | 1 | 2 | 5 | H
Gather historical data on tablet ordering process |  | 3 | 1 | 3 | 5 | H
Align and evaluate stakeholders |  | 14.5 | 1 | 14 | 30 | M
Calculate projections and enhancements |  | 12.5 | 5 | 10 | 30 | L
Interview members of the staff |  | 6.1667 | 2 | 5 | 15 | M
Create project charter (scope and goals) |  | 15.5 | 7 | 14 | 30 | M
Schedule kick off meeting |  | 2.3333 | 1 | 2 | 5 | H
Sourcing
Research tablet options |  | 6 | 2 | 5 | 14 | H
Generate quotes and review costs |  | 9.5 | 5 | 8 | 20 | H
Test out tablets |  | 2.3333 | 1 | 2 | 5 | H
Choose a tablet company |  | 8 | 4 | 8 | 12 | H
Vendor timeline and deliverables schedule |  | 15.5 | 7 | 14 | 30 | M
Planning
Create contracts and statements of work for vendors |  | 5 | 3 | 5 | 7 | M
Message about launch date to stakeholders |  | 2.3333 | 1 | 2 | 5 | M
Approval for custom branding and design package upgrade |  | 4.5 | 1 | 4 | 10 | H
Connect Sauce & Spoon marketing with Terrific Tablets |  | 2 | 1 | 2 | 3 | H
Schedule electrician |  | 4.1667 | 1 | 4 | 8 | M
Select menu items and coupon values to be featured on the tablets |  | 7.5 | 2 | 7 | 15 | L
Complete menu revamp |  | 18 | 7 | 14 | 45 | L
Order tablets |  | 2.3333 | 1 | 2 | 5 | M
Create social media and marketing campaign |  | 16.3333 | 14 | 20 | 4 | H
Create internal customer satisfaction surveys |  | 10.8333 | 5 | 10 | 20 | H
Create FOH and BOH employee training plan |  | 15.1667 | 5 | 14 | 30 | M
All staff meeting to introduce tablet program and get waitstaff buy-in |  | 1.5 | 1 | 1 | 4 | M
Create a procedure for securing tablets at the end of the night (at the table or in a safe) |  | 3 | 1 | 3 | 5 | H
Create launch day plan: staffing, troubleshooting, etc. |  | 13.5 | 5 | 14 | 20 | M
[MILESTONE] Tablets ready for installation
Installation
Tablets shipped and delivered |  | 9.5 | 6 | 9 | 15 | M
Complete wiring at all tables at Downtown and North |  | 4.6667 | 2 | 4 | 10 | L
Install tablets in the bar areas at the Downtown and North restaurant locations |  | 5.3333 | 2 | 4 | 14 | L
Enable GPS location services on each tablet |  | 1.6667 | 1 | 1 | 5 | M
Integrate tablets with POS software |  | 3 | 1 | 3 | 5 | L
Create messaging about payment portal security to display on the tablets |  | 3.5 | 2 | 3 | 7 | L
Test tablets and resolve any glitches |  | 4.5 | 1 | 4 | 10 | M
North test run |  | 2.3333 | 1 | 2 | 5 | M
Downtown test run |  | 2.3333 | 1 | 2 | 5 | M
[MILESTONE] Devices ready for training
Training
Training for management at Downtown location |  | 2.3333 | 1 | 2 | 5 | M
Training for management at North location |  | 2.3333 | 1 | 2 | 5 | M
Training for FOH and BOH at Downtown location |  | 4 | 1 | 4 | 7 | L
Training for FOH and BOH at North location |  | 4 | 1 | 4 | 7 | L
Test staff at Downtown and North locations |  | 2.3333 | 1 | 2 | 5 | M
[MILESTONE] Complete training
[PROJECT LAUNCH] Tablet and new menu rollout
Analyze the data to determine project success
Celebrate the launch of the tablets with the team
Hold a team retrospective

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Tabletop tech speeds up service and boosts profits, study says | Tabletop Tech Link | 2022-03-18 | Look into adding an option to play game on device for a small fee.
7 Vital Steps in a Successful Restaurant Technology Rollout | Rollout Tips | 2022-03-18 | Research all the data and metrics we are able to analyze through the tablet.

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Customer Satisfaction | customers would be satisfied by a faster, more efficient experience—and by having their orders made correctly. | Are customers receiving the correct orders? | 98% order accuracy | FALSE
|  | Are customers having a better dining experience with the tablets? | wait time decreased to ten minutes and food order arriving on time (a good average is eight minutes for appetizers and 12-15 minutes for entrees) | FALSE
|  | How quickly are customers learning how to navigate the tablets? | one-minute checkout time to determine usability | FALSE
|  | Do all the tablets work as expected? | less than 5% of customers who use tablets to report technical issues each week | FALSE
|  | How can we improve? |  | FALSE
|  | What is working and what’s not working? |  | FALSE
|  | Which goals are being met? |  | FALSE
|  | Who is benefiting? |  | FALSE
|  | What are the most common participant reactions? |  | FALSE
|  | Were there unintended outcomes? |  | FALSE
|  | What were the costs and benefits? |  | FALSE
|  | Are there any lessons to be learned? |  | FALSE
|  | Should we continue? |  | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
|  |  | Have you visited Sauce & Spoon in the past? | Yes/No | Yes | No
|  |  | How long did you wait for a table? | Multiple choice | No wait | 1-5 minutes | 5-10 minutes | 10-20 minutes | 20+ minutes
|  |  | On a scale of 1–5, where 1 is “very easy” and 5 is “not at all easy,” | Scaled | 1: Very satisfied | 2: Somewhat satisfied | 3: Neither satisfied nor dissatisfied | 4: Somewhat dissatisfied | 5: Very dissatisfied
|  |  | Did you encounter any technical difficulties while using the tablet? | Yes/No | Yes | No
|  |  | DId the tablet ordering system improve your dining experience? | Yes/No | Yes | No
|  |  | How long did your appetizer order take? | Multiple choice | 3-8 minutes | 8-12 minutes | 12-15 minues | 15+ minutes
|  |  | How long did your entree order take? | Multiple choice | 8-12 minutes | 12-16 minues | 16-20 minutes | 20-30 minutes | 30+ minutes
|  |  | When delivered, was your order accurate? | Yes/No | Yes | No
|  |  | What was your favorite part about the tablet ordering system? | Open-ended | open-ended
|  |  | You would recommend Sauce & Spoon to a friend. | True/False | TRUE | FALSE
|  |  | Are there any suggestions you have to improve your tablet dining experience? | Open-ended | open-ended